## Sheet1
Name of Project: Leave & Payroll Management System | Easy Techs
Project Execution Schedule
Key Project Milestones | Dates | 2021-09-18 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-10-29
| Days | 0 | 0 | 7 | 14 | 21 | 28 | 35 | 39
Kick-Off Meeting
Receipt of Master Data from Client
Receipt of Order Confirmation from Client
Design of Front end User Interface |  |  |  | Completed
Design and Development of Back end system
Software first cut discussion with Client (UI +Back End)
Deployment at Clients Office
Commissioning of Software
Note:
Activities Completed will be indicated by Green Color
Activities Under Progress will be indicated by Orange Color
Activities Yet to be started will be indicated by Blue Color
Activities Pending is highlighted in Red Color

## Sheet2
WEEK | 3 |  | NAME | HR & Payroll with ITE
Week | Target | MON (04) |  | TUE (05) | WED (06) | THU (07) | FRI (08) | SAT (09) | SUN (10)
04/10-10/10 | Complete Backend | Finalize DB |  | Report PF, ESIC | Report NEFT, Custom | Settings : Site, Password | Salary, Profile | Reserved | Reserved
Done
|  | Finalize DB |  | Add Employee | Add Record | Add Record | Generate Payslip | Reserved | Reserved
Done
WEEKLY SCHEDULE